# 2.2 CONTINUOUS IMPROVEMENT WORKSHEET

This worksheet is used to document the plan for what you want to improve in your orchard operation and the current status of the project. Outside of this, you will need to keep records of what you are doing and achieving – data, photos, test results, so that you can track progress over time. An example has been included to guide you in how this approach can be used.

It is important to note that items should be chosen that are realistically achievable – choose projects that are financially viable for you; however, it is OK to choose an area and put “cost/benefit exploration” as one of the activities - decisions can then be made about whether you can continue with that project or need to phase it over a longer timeline to fit in with your financial capability.

This method will need to be completed at least annually.

# EXAMPLES

| Targeted Outcome/Objective Look at current practices, packout and reject analysis, GG non-compliances, risk register items to assist in this decision. | Priority (High, Medium, Low) | Date Started | Activities/Actions to be Undertaken | Estimated date of completion Month and year | Current Status Not started (NS) In Progress (IP) Complete (C) | Measurements How will you record progress? | Person Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reduce waterlogged areas in the orchard to improve the soil by 2027 | High | January 2025 | - Cost-benefit analysis on wet areas, production/chemical use/time. - Investigate long-term best use of wet areas (wetland or production). - Investigate options for reducing waterlogging. - Implement solution. | April 2027 | IP | - Production records specific to waterlogged area/harvest separate from the surrounding area. - Use Ciba Geigy to measure tree health changes throughout each year. | Mrs ABC |

| Targeted Outcome/Objective* Look at current practices, packout and reject analysis, GG non-compliances, risk register items to assist in this decision. | Priority (High, Medium, Low) | Date Started | Activities/Actions to be Undertaken | Estimated date of completion* Month and year | Current Status* Not started (NS) In Progress (IP) Complete (C) | Measurements How will you record progress? | Person Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- |

If any of the above Continuous Improvement targets/objectives/activities/actions have not been completed by due date, or delayed or the goal changed - justify here:

_____________________________________________________

_____________________________________________________

_____________________________________________________